## General Project Activities
General Project Activity List
Date Occurred | Pre-Bid and Bid | Responsible Party | Notes
| Send Approval to Bid Letter to Owner and Design Professional | DBA Design Review
| Contact Design Professional to Submit Division Zero Documents | DBA Construction
| Send Division Zero Documents to DBA Construction | Design Professional
| Review Division Zero Documents | DBA Construction
| Coordinate Bid Date With Design Professional and Owner | DBA Construction
| Approve First Draft Division Zero Documents | DBA Construction
| Advertise Project | DBA Construction
| Send Draft Specification Book to Construction Section for Review | Design Professional
| Review Specification Book and Approve Reproduction | DBA Construction
| Send DBA Construction Specifications and Half Size Drawings | Design Professional
| Orchestrate Pre-Bid Conference | Design Professional
| Send DBA Construction Any Required Addenda for Approval | Design Professional
| Review and Approve Any Required Addenda | DBA Construction
| Approve Design Professional to Distribute Addenda | DBA Construction
| Send DBA Construction Proof of Addenda Disbursement | Design Professional
| Open Bids | DBA Construction
| Determine Responsiveness of Bidders | DBA Construction
| Send Owner Results of Bid and Request Determination to Award | DBA Construction
| Owner Determines Responsibleness of Low Bidder | Owner
| Send Determination to Award to DBA Construction | Owner
| Send Design Professional Approval to Issue Intent to Award | DBA Construction
| Send Intent to Award to Contractor Including Agreement Form, P&P Bond, Disclosure Etc. | Design Professional
| Negotiations | Responsible Party
| Send Owner Results of Bid and Request Determination to Award | DBA Construction
| Owner Determines Responsibleness of Low Bidder | Owner
| Send Determination to Award to DBA Construction | Owner
| Send Design Professional Approval to Initiate Negotiations | DBA Construction
| Send Letter of Intent to Negotiate to the Contractor | Design Professional
| Hold Negotiations | Owner and Design Professional
| Send Summary of Negotiations to DBA Design Review | Design Professional
| Review Negotiated Changes | DBA Design Review
| Send Letter to Owner Approving Negotiated Changes | DBA Design Review
| Send Owner Determination to Award Letter | DBA Construction
| Send Design Professional Approval to Issue Intent to Award | DBA Construction
| Send Intent to Award to Contractor Including Agreement Form, P&P Bond, Disclosure Etc. | Design Professional
| Contract Approval | Responsible Party
| Submits Required Contract Documents | Contractor
| Reviews Contract Document Submittal | Design Professional
| Approves Contract Documents and Forwards Them to Owner | Design Professional
| Reviews and Approves Contract Documents | Owner
| Forwards Contract Documents to DBA Construction for Review | Owner
| Reviews and Approves Contract Documents | DBA Construction
| Sends Approved Contract to Owner for Disbursement | DBA Construction
| Change Orders | Responsible Party
| Change Order Circumstance Arises | Any Contract Party
| Defines Scope of Change | Owner and Design Professional
| Coordinates Scope of Change With Owner | Design Professional
| Submits Scope to Contractor for Pricing | Design Professional
| Submits Pricing to Design Professional for Review | Contractor
| Reviews Pricing | Owner and Design Professional
| Sends Change Order to Contractor for Approval and Signature | Design Professional
| Approves Change Order and Forwards to Design Professional | Contractor
| Approves Change Order and Forwards to Owner | Design Professional
| Approves Change Order and Forwards to DBA Construction | Owner
| Reviews and Approves Change Order | DBA Construction
| Sends Approved Change Order to Owner for Disbursement | DBA Construction
| Substantial Completion | Responsible Party
| Notifies Design Professional the Project Meets Substantial Completion | Contractor
| Design Professional Schedules an Inspection With All Parties | Design Professional
| Project is Inspected | All Parties
| Punchlist is Created and Distributed | Design Professional
| Substantial Completion is Approved | Owner and Design Professional
| Substantial Completion Form is Forwarded to Contractor for Signature | Design Professional
| Substantial Completion Form is Forwarded to Owner for Signature | Design Professional
| Substantial Completion Form is Forwarded to DBA Construction for Approval | Owner
| Approves Substantial Completion | DBA Construction
| Sends Approved Documents to Owner for Disbursement | DBA Construction
| Final Payment | Responsible Party
| Punchlist is Completed | Contractor
| Request for Final Inspection is Submitted to Design Professional | Contractor
| Design Professional Schedules an Inspection With All Parties | Design Professional
| Project is Inspected | All Parties
| As Builts, Warranties, Operations Manuals Etc. are Submitted to Design Professional | Contractor
| Final Payment Documents are Submitted to Design Professional | Contractor
| Reviews and Approves All Submitted Closeout Documentation | Design Professional
| Submits As Builts, Warranties, Operations Manuals Etc. to Owner | Design Professional
| Final Payment Documents are Submitted to Owner for Review and Approval | Design Professional
| Final Payment Documents Are Submitted to DBA Construction | Owner
| Approves Final Payment | DBA Construction
| Sends Approved Documents to Owner for Disbursement | DBA Construction
| Project CD-Rom is Created and Submitted to Owner and DBA Construction | Design Professional

## Contract Approval
Agreement Form
Intent to Award Letter
Low Bidder Awarded Contract
Does Contract Amount Match Bid or Negotiated Amount
If Negotiated Does it Have ABA Design Review Approval
Does the Contract Have the Correct Agency Name
Agreement Form Signed By Contractor
Agreement Form Signed By Owner
* | If Contractor's a Corporation is the Person Authorized to Execute Document
Does the Completion Date Match the Bid Documents
Performance and Payment Bond
Contractor's Company Name Correct
Contractor's Signature
* | If Contractor's a Corporation is the Person Authorized to Execute Document
Verify Contract Effective Date Matches Agreement Form
Power of Attorney for Agent Accompanies Bond
Bond Filed in County Courthouse
* | Agent and Surety Company Licensed and Authorized in State
Insurance
Effective Dates
Expiration Dates
* | Company Authorized to Conduct Business in State
Owner Has Reviewed Policy and Approved Coverage
Match Insurance Coverage With Contract Documents
Other Documents
Certified Bid Tab
Disclosure Statement From Contractor EO 98-04
Contractor's Illegal Immigration Certification
* DBA Construction Will Verify

## Change Order Approval
Change Order Form
Check Project Folder to Ensure Proper Change Order Number
Check Project Folder to Ensure Proper Change Order Number
DBA Project Name and Number is Correct
Owner Name is Correct
EO 98-04 Disclosure Statement Checkbox is Check
Method of Payment Checkbox is Checked
The Reason for Change Order Checkbox's are Checked
Justification is Summarized and Cost is Listed
Original Contract Amount is Correct
Previous Change Order Amount is Correct
Current Change Order Amount is Correct
New Change Order Amount is Correct
If Contract Time is Changing Ensure Number of Days Match Date Listed on Form
The Contractor, Design Professional, and Owner Has Signed Change Order
If a Corporation, the Person Signing For Contractor is Authorized
Documentation
Scope of Changes From Design Professional (Plans and Specifications)
Copy of Request for Pricing From Design Professional
Contractor's Breakdown and Summary of Costs
EO 98-04 Disclosure Statements of Any New Subcontractor's
Statement of Subcontractor's Contract Cost

## Final Payment Approval
Require Documents
Final Application for Payment
Check Current Contract Amount
Check Previous Payment to Verify Payment Amount is Correct
Verify All Work (punchlist also) is Complete to Include All Change Orders
Previously Approved Certificate of Substantial Completion (DBA Form)
Approved by DBA Construction
Certificate of Final Completion (DBA Form)
Signed by Contractor, Design Professional, Owner, and DBA Inspector
Contractor Release of Claims (DBA Form)
Signed by Contractor
Surety Consent of Surety (DBA Form Preferred)
Signed by Agent
Agent Power of Attorney Attached
Agency Request For Final Payment (DBA Form)
Check Current Contract Amount
Check Previous Payment to Verify Payment Amount is Correct
Verify All Work is Complete to Include All Change Orders
Verify Retainage Was Properly Assessed and Released
Summary of Determination of Liquidated Damages (in either case)
Design Professional's Closeout Certification
All Applicable Checkbox's Certified and Documentation Received
Review "ABA's Project Closeout Guide" for Additional Information
Other Documents (DBA does not need to approve final payment)
Contractor's One Year Warranty
Contractor's Two Year Roof Warranty
Manufactures Roof Warranty
Maintenance and Operation Manuals
As Built Drawings
CD-Rom From Design Professional
Contractor Provided Training and Materials
Inspection Reports for Building, Systems, and Equipment
Review "DBA's Project Closeout Guide" for Additional Information